1) Pre-Wedding Activities

1. **Initial Planning**
   * Confirm wedding date and venue (1 day)
   * Set budget and financial planning (2 days)
2. **Guest List Preparation**
   * Compile a guest list from both families (3 days)
   * Gather contact information (emails, phone numbers) for invitations (2 days)
3. **Venue Arrangements**
   * Research and finalize the outdoor ceremony and reception venue (15 days)
   * Book the venue (1 day)
4. **Wedding Party Selection**
   * Confirm bridesmaids and groomsmen (3 days)
   * Discuss roles for flower girls and ring bearer (1 day)
5. **Attire Selection**
   * Shop for wedding dress and tuxedo (27 days)
   * Schedule fittings for dress and tuxedo (2 days)
6. **Catering and Food Planning**
   * Decide on the menu for the reception (14 days)
   * Arrange tastings with caterers (5 days)
7. **Entertainment Arrangements**
   * Book a DJ or live band for the reception (7 days)
   * Plan music for the ceremony (2 days)
8. **Photography and Videography**
   * Research and book a photographer and videographer (2 days)
9. **Floral Arrangements**
   * Choose flowers for bouquets, centerpieces, etc. (7 days)
   * Finalize orders with florists (3 days)
10. **Cake Selection**
    * Schedule cake tasting appointments (5 days)
11. **Transportation Arrangements**
    * Organize transportation for guests if necessary (5 days)
12. **Rehearsal Dinner Planning**
    * Select a date, time, and venue for rehearsal dinner (7 days)
13. **Finalize Wedding Day Schedule**
    * Create a timeline for the wedding day events (1 day)
14. **Confirmation with Vendors**
    * Confirm all details with vendors one week prior to the wedding (1 day)
15. **Final Preparations**
    * Pack items needed for the wedding day, including attire, accessories, etc. (1 day)
    * Prepare gratuity envelopes for vendors (1 day)
16. **Post-Wedding Tasks**
    * Arrange for gift collection and sorting after the ceremony (1 day)

2) Activity Responsibilities

1. **Initial Planning**
   * **Confirm wedding date and venue**: Tony and Peggy Sue
   * **Set budget and financial planning**: Tony and Peggy Sue
2. **Guest List Preparation**
   * **Compile a guest list from both families**: Tony and Peggy Sue
   * **Gather contact information for invitations**: Event Committee (family members)
3. **Venue Arrangements**
   * **Research and finalize outdoor ceremony and reception venue**: Event Committee
   * **Book the venue**: Tony and Peggy Sue
4. **Wedding Party Selection**
   * **Confirm bridesmaids and groomsmen**: Tony and Peggy Sue
   * **Discuss roles for flower girls and ring bearer**: Tony and Peggy Sue
5. **Attire Selection**
   * **Shop for wedding dress and tuxedo**: Peggy Sue (dress) and Tony (tuxedo)
   * **Schedule fittings for dress and tuxedo**: Peggy Sue and Tony
6. **Catering and Food Planning**
   * **Decide on the menu for the reception**: Tony, Peggy Sue, and Event Committee
   * **Arrange tastings with caterers**: Event Committee
7. **Entertainment Arrangements**
   * **Book a DJ or live band for the reception**: Event Committee
   * **Plan music for the ceremony**: Event Committee
8. **Photography and Videography**
   * **Research and book a photographer and videographer**: Tony and Peggy Sue
9. **Floral Arrangements**
   * **Choose flowers for bouquets, centerpieces, etc.**: Peggy Sue (with input from Tony)
   * **Finalize orders with florists**: Event Committee
10. **Cake Selection**
    * **Schedule cake tasting appointments**: Peggy Sue (with input from Tony)
11. **Transportation Arrangements**
    * **Organize transportation for guests if necessary**: Event Committee
12. **Rehearsal Dinner Planning**
    * **Select date, time, and venue for rehearsal dinner**: Tony and Peggy Sue
13. **Finalize Wedding Day Schedule**
    * **Create a timeline for the wedding day events**: Event Committee
14. **Confirmation with Vendors**
    * **Confirm all details with vendors one week prior to the wedding**: Event Committee
15. **Final Preparations**
    * **Pack items needed for the wedding day**: Tony and Peggy Sue
    * **Prepare gratuity envelopes for vendors**: Tony and Peggy Sue
16. **Post-Wedding Tasks**
    * **Arrange for gift collection after the ceremony**: Tony, Peggy Sue, and parents

3)

START

|

v

1. Confirm wedding date and venue (Tony, Peggy Sue)

|

v

2. Set budget and financial planning (Tony, Peggy Sue)

|

v

3. Compile guest list (Tony, Peggy Sue)

|

v

4. Research and finalize venue (Event Committee)

|

v

5. Book the venue (Tony, Peggy Sue)

|

v

6. Confirm wedding party (Tony, Peggy Sue)

|

v

7. Shop for wedding dress and tuxedo (Peggy Sue, Tony)

| |

| v

| 8. Schedule fittings (Peggy Sue, Tony)

| |

| v

| 9. Choose flowers (Peggy Sue)

| |

| v

| 10. Finalize orders with florists (Event Committee)

| |

| v

11. Decide on menu for reception (Tony, Peggy Sue, Event Committee)

|

v

12. Arrange tastings with caterers (Event Committee)

|

v

13. Book entertainment (Event Committee)

|

v

14. Research and book photographer/videographer (Tony, Peggy Sue)

|

v

15. Plan transportation arrangements (Event Committee)

|

v

16. Rehearsal dinner planning (Tony, Peggy Sue)

|

v

17. Create wedding day timeline (Event Committee)

|

v

18. Confirm details with vendors (Event Committee)

|

v

19. Pack items for wedding day (Tony, Peggy Sue)

|

v

20. Arrange gift collection after ceremony (Tony, Peggy Sue, Parents)

|

v

END